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“”Social Heroes”
KA2 – Capacity building activities


“Social heroes” is project about social entrepreneurship which aims to foster and empower the active participation of the young people in the civil society trough their inclusion in the social economy. This will be achieved by giving various tools for the development of social impact enterprises as a way to fight the youth unemployment. The idea of “Zavod za idei” Association is to elaborate a strategy for development of the entrepreneurial spirit and active participation in the society among the young people and to implement this strategy on local level. 


The process: 
	Type of mobility
	Country 
	Total number of participants 
	From
	To
	Duration
	Responsible

	APV
	Bulgaria
	25
	16.10.2015
	19.10.2015
	3 days
	Bulgaria

	T.C.
	Bulgaria
	42
	08.01.2016
	13.01.2016
	7 days
	Bulgaria

	Assessment meeting (AM)
	Ireland
	17
	05.05.2016
	08.05.2016
	4 days
	Ireland 

	AM
	Serbia
	17
	21.05.2016
	24.05.2016
	4 days
	Serbia

	AM
	Bulgaria
	17
	03.06.2016
	06.06.2016
	4 days
	Bulgaria

	AM
	Albania
	17
	24.06.2016
	27.06.2016
	4 days
	Albania

	AM
	Turkey
	17
	15.07.2016
	18.07.2016
	4 days
	Turkey

	AM
	Italy
	17
	25.07.2016
	28.07.2016
	4 days
	Italy

	AM
	Spain
	17
	06.08.2016
	09.08.2016
	4 days
	Spain

	AM
	Georgia
	17
	22.08.2016
	25.08.2016
	4days
	Georgia

	AM 
	Egypt
	17
	05.09.2016
	08.09.2016
	4 days
	Egypt

	AM
	Sweden
	17
	26.09.2016
	29.09.2016
	4 days
	Sweden

	Final meeting
	Bulgaria
	25
	21.10.2016
	23.10.2016
	3 days
	Bulgaria


*Some dates or places could be changed!








Partner responsibilities:

· Participation in an APV (October 2015)
· The organization of two informational seminars on local level on the following themes:
-Active participation and youth unemployment (November 2015)
-Social economy and social entrepreneurship (December 2015)
· Participation in a T.C., which aims to elaborate a strategy for development of the entrepreneurial spirit and active participation in the society among the young people.
· Implementation of the latter strategy on local level working with the group of young people who the partner organizations target. (January – April 2016)
· Participation in monitoring and assessment meetings in the countries of all participating organizations. (May – September 2016)
· Participation in a Final Conference which is going to be dedicated on creation informational material, case studies and other resources; evaluation and planning of future actions and partnerships relevant to the core idea of the project. (October 2016)
· Publishing results, materials, articles etc. on the official website during the whole project
· [bookmark: _GoBack]Preparation and execution of their duties 
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