“”Social Heroes”

KA2 – Capacity building activities

“Social heroes” is project about social entrepreneurship which aims to foster and empower the active participation of the young people in the civil society trough their inclusion in the social economy. This will be achieved by giving various tools for the development of social impact enterprises as a way to fight the youth unemployment. The idea of “Zavod za idei” Association is to elaborate a strategy for development of the entrepreneurial spirit and active participation in the society among the young people and to implement this strategy on local level.

The process:

| Type of mobility | Country | Total number of participants | From | To | Duration | Responsible |
| --- | --- | --- | --- | --- | --- | --- |
| APV | Bulgaria | 25 | 16.10.2015 | 19.10.2015 | 3 days | Bulgaria |
| T.C. | Bulgaria | 42 | 08.01.2016 | 13.01.2016 | 7 days | Bulgaria |
| Assessment meeting (AM) | Ireland | 17 | 05.05.2016 | 08.05.2016 | 4 days | Ireland |
| AM | Serbia | 17 | 21.05.2016 | 24.05.2016 | 4 days | Serbia |
| AM | Bulgaria | 17 | 03.06.2016 | 06.06.2016 | 4 days | Bulgaria |
| AM | Albania | 17 | 24.06.2016 | 27.06.2016 | 4 days | Albania |
| AM | Turkey | 17 | 15.07.2016 | 18.07.2016 | 4 days | Turkey |
| AM | Italy | 17 | 25.07.2016 | 28.07.2016 | 4 days | Italy |
| AM | Spain | 17 | 06.08.2016 | 09.08.2016 | 4 days | Spain |
| AM | Georgia | 17 | 22.08.2016 | 25.08.2016 | 4days | Georgia |
| AM | Egypt | 17 | 05.09.2016 | 08.09.2016 | 4 days | Egypt |
| AM | Sweden | 17 | 26.09.2016 | 29.09.2016 | 4 days | Sweden |
| Final meeting | Bulgaria | 25 | 21.10.2016 | 23.10.2016 | 3 days | Bulgaria |

*Some dates or places could be changed!

Partner responsibilities:

- Participation in an APV (October 2015)

- The organization of two informational seminars on local level on the following themes:

-Active participation and youth unemployment (November 2015)

-Social economy and social entrepreneurship (December 2015)

- Participation in a T.C., which aims to elaborate a strategy for development of the entrepreneurial spirit and active participation in the society among the young people.

- Implementation of the latter strategy on local level working with the group of young people who the partner organizations target. (January – April 2016)

- Participation in monitoring and assessment meetings in the countries of all participating organizations. (May – September 2016)

- Participation in a Final Conference which is going to be dedicated on creation informational material, case studies and other resources; evaluation and planning of future actions and partnerships relevant to the core idea of the project. (October 2016)

- Publishing results, materials, articles etc. on the official website during the whole project

- Preparation and execution of their duties