- Kick off meeting : Month 2 – July 2019– 2 days

- On-line survey:  M3 – M4 (August – October 2019_

- Strategy: M5 – M7 (November 2019 – January 2020)

- Interim meeting – M8 (Febr 2020) – 2 days

- Training course – M12 (June 20200 – 7 days

- Local plans – M13 – M16 (July – October 2020)

- On line platform: M6 -  M8 (Dec – Febr 2019 – 2020)

- APP Game: M8 – M 10 ( February- April 2020_

- Interim meeting 2: M 11 (May 2020)

- Mutiplier events: M17 – M 18 (Nov – December 2020)

- Final Conference: M 20 (Febr 2021) – 1 day

- Final meeting: M20 (Febr 2021) – 1 day