## Sheet1
New overview Don't Ignore, Act - Mobility of Youth Workers 2023
Activity/Month | August | September | October | November | December | January | February | March | April | May | June |  | July | August | September
Partners selection
Mandates sent and NA contract signed
Internal Agreements signed
Info pack/app. form designed and shared
Editable documents and DRIVE folder
Tool and documents
Official Facebook/Instagram page start
Desing materials
Participants' selection
Pre-departure trainings
Flight tickets
Facebook groups
Learning Agreements and other docs
Mobility | [11 empty] | 27 - 05
Reimbursement transactions
Dissemination workshops/meetings
Final Report/Evaluation
*Editable documents and DRIVE folder - project implementation graphic, participants list, participants travel details
*Tools and documents - Tricks&Tips, How to get here
*Materials - Roll-up, poster, pens, stickers, brochures, welcome letter, doors posters, badges, schedule
*Logistics - accomodation agreement, local transportation, catering, contact UNHCR office/arrange visit, dinner in the city
*Other docs - learning agreements, participants list, personal statement, reimbursement forms,